## 17-239
Task Name | Estimate time( hour) | Taken by | Actual Time | Status | Date Doing | Note | Problem
Requirement analyze | 5 | Hua Vinh Khang | 6 | Done | 2020-10-19
Draw Conceptual Diagram | 3 | Hua Vinh Khang | 1.5 | Done | 2020-10-19
Draw Use-case Diagram | 2 | Hua Vinh Khang | 1 | Done | 2020-11-01
Create Database Query | 3 | Hua Vinh Khang | 2 | Done | 2020-10-19
Create Physical Diagram | 1 | Hua Vinh Khang | 1 | Done | 2020-10-19
Insert data to Database | 2 | Hua Vinh Khang | 1 | Done | 2020-10-19
Learning MVC model in Web Service C# | 12 | Hua Vinh Khang | 8 | Done | 14/10/2020-16/10/2020
Code Login Function | 2 | Hua Vinh Khang | 1 | Done | 2020-10-19
Code LoadList Products Function | 2 | Hua Vinh Khang | 2 | Done | 2020-10-20
Code AddToCart Function | 2 | Hua Vinh Khang | 1 | Done | 2020-10-31
Code UpdateCart Function | 2 | Hua Vinh Khang | 1 | Done | 2020-10-31
Code RemoveFromCart Function | 2 | Hua Vinh Khang | 0.5 | Done | 2020-10-31
Code ConfirmCart Function | 4 | Hua Vinh Khang | 1.5 | Done | 2020-10-31
Write Docs (Review 1) | 16 | Hua Vinh Khang | 12 | Done | 2020-11-10
Create Slide | 8 | Hua Vinh Khang | 3 | Done | 2020-11-12
Create User-Guide | 6 | Hua Vinh Khang | 5 | Done | 2020-11-12
Write Use-Case Detail (Cart) | 0.5 | Hua Vinh Khang | 0.5 | Done | 2020-11-07
Total (%) | 43.28 |  | 46.6
Learning MVC model in Web Service C# | 12 | Le Dat Anh Khoi | 8 | Done | 2020-10-21
Code Create Account Function | 2 | Le Dat Anh Khoi | 1 | Done | 2020-10-25
Code Update Account (Admin - Customer) | 2 | Le Dat Anh Khoi | 1 | Done | 2020-10-25
Learning Validation with Jquery, AJAX | 5 | Le Dat Anh Khoi | 3 | Done | 2020-11-01
Code Validate with Jquery, AJAX | 2 | Le Dat Anh Khoi | 2 | Done | 2020-11-03
Create Class Diagram | 10 | Le Dat Anh Khoi | 4 | Done | 2020-11-07
Write Use-Case Detail (Update Account) | 10 | Le Dat Anh Khoi | 2 | Done | 2020-11-08
Total (%) | 25.67 |  | 20.39
Learning MVC model in Web Service C# | 12 | Nguyen Duc Trung | 9 | Done | 14/10/2020-16/10/2020
Draw ERD | 6 | Nguyen Duc Trung | 6 | Done | 2020-10-28
Code Search Order By Name (Admin) | 3.5 | Nguyen Duc Trung | 2 | Done | 2020-11-03
Code Track Orders (Admin, Customer) | 7 | Nguyen Duc Trung | 3 | Done | 2020-11-03
Write Use-Case Detail (Track Orders) | 4 | Nguyen Duc Trung | 3 | Done | 2020-11-04
Write Entity Description & Table Design in Docs | 6 | Nguyen Duc Trung | 2.5 | Done | 2020-11-04
Write Task Sheet | 6 | Nguyen Duc Trung | 3 | Done | 2020-11-08
Write Product Backlog | 8 | Nguyen Duc Trung | 5 | Done | 2020-11-10
Total (%) | 31.34 |  | 32.52
Learning MVC model in Web Service C# | 12 | Dinh Nhu Hieu | 8 | Done | 14/10/2020 -16/10/2020
Code Create Product | 1 | Dinh Nhu Hieu | 2 | Done | 2020-10-29
Code Update Product | 1 | Dinh Nhu Hieu | 1 | Done | 2020-10-29
Code Search Products (Brand, Category, Name) | 2 | Dinh Nhu Hieu | 2 | Done | 2020-10-29
Write Use-Case Detail (Search Productss) | 2 | Dinh Nhu Hieu | 2.5 | Done | 2020-11-03
Write Use-Case Detail (Create Product) | 2 | Dinh Nhu Hieu | 1.5 | Done | 2020-11-03
Write Use-Case Detail (Update Product) | 1 | Dinh Nhu Hieu | 0.5 | Done | 2020-11-04
Code Front-end | 10 | Dinh Nhu Hieu | 13 | Done | 07-11-2020 - 12-11-2020
Write Interface(Docs) | 3 | Dinh Nhu Hieu | 2.5 | Done | 2020-11-12
Total (%) | 20.3 |  | 16.99
Sum of Estimate Hours | 103.29 | Sum of Actual Hours | 102.01